## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Saloni Kumari | 02-07-2026 | Streamlit UI layout misalignment on smaller screens | Sprint 1 | Saloni Kumari | User Interface | Adjusted CSS and column widths for responsive layout | 02-07-2026 | Closed | Fixed layout responsiveness
2 | Saloni Kumari | 03-07-2026 | Relevance Agent returning inconsistent scores for similar inputs | Sprint 1 | Saloni Kumari | Logical | Refined similarity threshold and added normalization logic | 03-07-2026 | Closed | Evaluation logic stabilized
3 | Saloni Kumari | 03-07-2026 | Accuracy Agent failing on edge cases with partial matches | Sprint 1 | Saloni Kumari | Logical | Added fuzzy matching and partial credit scoring | 04-07-2026 | Closed | Edge cases handled
4 | Saloni Kumari | 04-07-2026 | Hallucination Agent flagging correct information as hallucinated | Sprint 1 | Saloni Kumari | Logical | Tuned keyword overlap threshold and added context checks | 05-07-2026 | Closed | False positive rate reduced
5 | Saloni Kumari | 05-07-2026 | Completeness Agent not detecting missing sub-points | Sprint 1 | Saloni Kumari | Logical | Enhanced section-based comparison logic | 05-07-2026 | Closed | Completeness detection improved
6 | Saloni Kumari | 06-07-2026 | Plotly charts overlapping on the dashboard | Sprint 1 | Saloni Kumari | User Interface | Updated Plotly configuration and fixed container spacing | 06-07-2026 | Closed | Chart alignment fixed
7 | Saloni Kumari | 07-07-2026 | Report download button not generating CSV correctly | Sprint 1 | Saloni Kumari | Logical | Fixed DataFrame export formatting and encoding issues | 07-07-2026 | Closed | CSV/TXT download working
8 | Saloni Kumari | 08-07-2026 | Evaluation history not persisting between sessions | Sprint 1 | Saloni Kumari | Logical | Implemented session state management for history tracking | 08-07-2026 | Closed | History persistence added
9 | Saloni Kumari | 08-07-2026 | Dashboard cards styling inconsistent across browsers | Sprint 1 | Saloni Kumari | User Interface | Standardized CSS with cross-browser compatible styles | 09-07-2026 | Closed | Cross-browser compatibility achieved
10 | Saloni Kumari | 09-07-2026 | Documentation missing API endpoint details for future LLM integration | Sprint 1 | Saloni Kumari | Maintainability | Added API integration roadmap and placeholder modules in documentation | 09-07-2026 | Closed | Documentation updated
11 | Saloni Kumari | 14-07-2026 | Windows path length limit (WinError 206) blocked torch/torchvision installation due to long WindowsApps Python install path | Sprint 2 | Saloni Kumari | Environment | Created an isolated virtual environment at a short path (C:\rag-env) to avoid exceeding Windows MAX_PATH limit | 14-07-2026 | Closed | Resolved by migrating to a clean short-path virtual environment
12 | Saloni Kumari | 14-07-2026 | Hugging Face dataset/model downloads failing intermittently (xet protocol timeouts, DNS resolution errors on some CDNs) | Sprint 2 | Saloni Kumari | Environment | Disabled xet via HF_HUB_DISABLE_XET env variable; used jsDelivr GitHub mirror for TruthfulQA dataset as a fallback | 14-07-2026 | Closed | Downloads now complete reliably over plain HTTPS
13 | Saloni Kumari | 14-07-2026 | RAG retriever returning irrelevant reference answers (negative similarity score) for questions outside the knowledge base domain | Sprint 2 | Saloni Kumari | Logical | Added a similarity threshold (0.3) so low-confidence retrievals are rejected and the user is prompted to enter a reference manually | 20-07-2026 | Closed | Prevents irrelevant context from being fed into evaluation
14 | Saloni Kumari | 16-07-2026 | Accuracy Judge (LLM) used its own outside knowledge instead of the provided evidence, incorrectly validating a response against unrelated evidence | Sprint 3 | Saloni Kumari | Logical | Rewrote system prompt to strictly forbid outside knowledge and require a low score when evidence does not address the response topic | 20-07-2026 | Closed | Verified fixed with a deliberate unrelated-evidence test case
15 | Saloni Kumari | 16-07-2026 | Hallucination Judge (LLM) fabricated supporting details from its own training knowledge instead of flagging them as unsupported claims | Sprint 3 | Saloni Kumari | Logical | Rewrote system prompt to require strict claim-by-claim comparison against only the exact evidence text provided | 16-07-2026 | Closed | Verified fixed against mentor-provided Newton/gravity example

## Sheet2
Logical
User Interface
Maintainability
Standards
Others