## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As a user, I want to enter a question so that the AI response can be evaluated. | Must Have | None | Saloni Kumari | Done
Sprint 1 | Sprint 1 | US02 | As a user, I want to enter the AI-generated response for evaluation. | Must Have | US01 | Saloni Kumari | Done
Sprint 1 | Sprint 1 | US03 | As a user, I want to provide a reference answer to compare with the AI response. | Must Have | US02 | Saloni Kumari | Done
Sprint 1 | Sprint 1 | US04 | As a user, I want the system to evaluate the relevance of the AI response. | Must Have | US02 | Saloni Kumari | Done
Sprint 1 | Sprint 1 | US05 | As a user, I want the system to evaluate the accuracy of the AI response. | Must Have | US02 | Saloni Kumari | Done
Sprint 1 | Sprint 1 | US06 | As a user, I want the system to detect hallucinated information. | Must Have | US02 | Saloni Kumari | Done
Sprint 1 | Sprint 1 | US07 | As a user, I want the system to evaluate the completeness of the response. | Must Have | US02 | Saloni Kumari | Done
Sprint 1 | Sprint 1 | US08 | As a user, I want to see an overall evaluation score and verdict. | Must Have | US04, US05, US06, US07 | Saloni Kumari | Done
Sprint 1 | Sprint 1 | US09 | As a user, I want to view graphs and charts for evaluation scores. | Should Have | US08 | Saloni Kumari | Done
Sprint 1 | Sprint 1 | US10 | As a user, I want to download the evaluation report in CSV and TXT format. | Should Have | US08 | Saloni Kumari | Done
Sprint 1 | Sprint 1 | US11 | As a user, I want to view previous evaluation history. | Could Have | US10 | Saloni Kumari | Done
Sprint 1 | Sprint 1 | US12 | As a user, I want an attractive and interactive dashboard for better user experience. | Could Have | US09 | Saloni Kumari | Done
Sprint 1 | Sprint 1 | US13 | As a developer, I want the project documentation to be maintained throughout development. | Must Have | None | Saloni Kumari | Done
Sprint 1 | Sprint 1 | US14 | As a developer, I want to test every evaluation module before deployment. | Must Have | US04–US12 | Saloni Kumari | Done
Sprint 1 |  | US15 | As a developer, I want future integration with LLM APIs (OpenAI/Gemini) for real-time evaluation. | Won't Have (Current Sprint) | None | Saloni Kumari | Future

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US01 | T1 | Project setup and folder structure | 01-07-2026 | 01-07-2026 | Saloni Kumari | Development | Done | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US01 | T2 | Design Streamlit user interface | 01-07-2026 | 02-07-2026 | Saloni Kumari | Development | Done | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US02 | T3 | Implement Relevance Agent | 02-07-2026 | 03-07-2026 | Saloni Kumari | Development | Done | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T4 | Implement Accuracy Agent | 03-07-2026 | 04-07-2026 | Saloni Kumari | Development | Done | 5 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | T5 | Implement Hallucination & Completeness Agents | 04-07-2026 | 06-07-2026 | Saloni Kumari | Development | Done | 8 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | T6 | Create dashboard, charts, evaluation report and testing | 06-07-2026 | 08-07-2026 | Saloni Kumari | Development & Testing | Done | 10 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US06 | T7 | Documentation and GitHub update | 08-07-2026 | 09-07-2026 | Saloni Kumari | Documentation | Done | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Yesterday's Work | Today's Plan | Impediments | Action Taken
Sprint 1 | Day 1 | Created project structure and installed required libraries. | Design the Streamlit UI. | None | Started UI development.
Sprint 1 | Day 2 | Completed the basic Streamlit interface. | Implement Relevance and Accuracy Agents. | Minor issue with Streamlit layout. | Adjusted UI layout and continued development.
Sprint 1 | Day 3 | Developed Relevance and Accuracy Agents. | Implement Hallucination and Completeness Agents. | Difficulty tuning evaluation logic. | Modified evaluation functions after testing.
Sprint 1 | Day 4 | Completed all evaluation agents. | Integrate agents with the dashboard and create charts. | Plotly chart alignment issue. | Updated Plotly configuration and fixed dashboard layout.
Sprint 1 | Day 5 | Dashboard and report generation completed. | Perform testing, documentation, and GitHub updates. | No major issues. | Fixed minor bugs, completed documentation, and uploaded the project to GitHub.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 01-07-2026 | 09-07-2026 | Saloni Kumari | Building modular AI agents | Writing large blocks of code without testing | Testing each module individually | Adopted modular development and frequent testing.
2 | Sprint 1 | 01-07-2026 | 09-07-2026 | Saloni Kumari | Improving Streamlit UI | Using basic default UI | Designing a professional dashboard | Added custom CSS, cards, charts, and improved layout.
3 | Sprint 1 | 01-07-2026 | 09-07-2026 | Saloni Kumari | Maintaining project documentation | Delaying documentation until the end | Updating documentation after every feature | Kept Agile documents and GitHub updated regularly.
4 | Sprint 1 | 01-07-2026 | 09-07-2026 | Saloni Kumari | Testing before final submission | Ignoring small UI issues | Performing complete end-to-end testing | Fixed UI alignment, report generation, and history tracking issues.
5 | Sprint 1 | 01-07-2026 | 09-07-2026 | Saloni Kumari | Improving code readability | Writing repetitive code | Keeping code modular and reusable | Refactored code into separate agents and orchestrator modules.