## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Saloni Kumari | 02-07-2026 | Streamlit UI layout misalignment on smaller screens | Sprint 1 | Saloni Kumari | User Interface | Adjusted CSS and column widths for responsive layout | 02-07-2026 | Closed | Fixed layout responsiveness
2 | Saloni Kumari | 03-07-2026 | Relevance Agent returning inconsistent scores for similar inputs | Sprint 1 | Saloni Kumari | Logical | Refined similarity threshold and added normalization logic | 03-07-2026 | Closed | Evaluation logic stabilized
3 | Saloni Kumari | 03-07-2026 | Accuracy Agent failing on edge cases with partial matches | Sprint 1 | Saloni Kumari | Logical | Added fuzzy matching and partial credit scoring | 04-07-2026 | Closed | Edge cases handled
4 | Saloni Kumari | 04-07-2026 | Hallucination Agent flagging correct information as hallucinated | Sprint 1 | Saloni Kumari | Logical | Tuned keyword overlap threshold and added context checks | 05-07-2026 | Closed | False positive rate reduced
5 | Saloni Kumari | 05-07-2026 | Completeness Agent not detecting missing sub-points | Sprint 1 | Saloni Kumari | Logical | Enhanced section-based comparison logic | 05-07-2026 | Closed | Completeness detection improved
6 | Saloni Kumari | 06-07-2026 | Plotly charts overlapping on the dashboard | Sprint 1 | Saloni Kumari | User Interface | Updated Plotly configuration and fixed container spacing | 06-07-2026 | Closed | Chart alignment fixed
7 | Saloni Kumari | 07-07-2026 | Report download button not generating CSV correctly | Sprint 1 | Saloni Kumari | Logical | Fixed DataFrame export formatting and encoding issues | 07-07-2026 | Closed | CSV/TXT download working
8 | Saloni Kumari | 08-07-2026 | Evaluation history not persisting between sessions | Sprint 1 | Saloni Kumari | Logical | Implemented session state management for history tracking | 08-07-2026 | Closed | History persistence added
9 | Saloni Kumari | 08-07-2026 | Dashboard cards styling inconsistent across browsers | Sprint 1 | Saloni Kumari | User Interface | Standardized CSS with cross-browser compatible styles | 09-07-2026 | Closed | Cross-browser compatibility achieved
10 | Saloni Kumari | 09-07-2026 | Documentation missing API endpoint details for future LLM integration | Sprint 1 | Saloni Kumari | Maintainability | Added API integration roadmap and placeholder modules in documentation | 09-07-2026 | Closed | Documentation updated

## Sheet2
Logical
User Interface
Maintainability
Standards
Others